## sprint 2 sprint backlog_v2
Issue Type | Issue key | Summary | Assignee | Status | Resolution | Description | Custom field (Acceptance Criteria) | Custom field (Work Done)
Story | MARKETMAG-75 | Check for existing models | Abed Nael Mussawi | Done | Done | *As a/an* experienced investor, *I Want* to be prompted if a stock I chose has no existing model, *So that* I can decide if I want to wait to train a model or not | # When user clicks on get prediction for a stock that does not have a model, the application will display a prompt # The prompt will tell users the stock model does not exist # Tensorflow models are saved locally in the file system. The database will point to the paths of these models. | # Added a function to save the model to the local files. # Added a function to load saved files from the local files and implemented both functions in the prediction view. # Developed a Django model that creates a database table where the path to locally saved trained models is stored.
Subtask | MARKETMAG-68 | implement the Django's model to save the paths for TensorFlow models. | Abed Nael Mussawi | Done | Done | Tensorflow models are saved locally in the file system. The database will point to the paths of these models.
Subtask | MARKETMAG-54 | Check if Django database(model) can save trained AI stock models | Abed Nael Mussawi | Done | Done | Save model in local memory, django DB hold path information.
Subtask | MARKETMAG-53 | Split up page_test view into model training and get prediction views | Abed Nael Mussawi | Done | Done | Add andrew as cosign
Task | MARKETMAG-34 | Sprint 2 Application Test Cases | Abed Nael Mussawi | In Progress |  | # Research how Django implements tests. # Create some component level tests for backend # Set of steps to test front end | # Design tests using Djanjo’s framework to test the functionality of the application # Running these tests and reporting the tests findings # Manually testing the website page, making sure that all the buttons and functionalities operate as intended | # researched Django’s test methodology. # implemented some component-level tests in the test.py file of the project # Manually tested the website and made sure everything is working as intended
Story | MARKETMAG-70 | Train AI models for stocks of interest | Andrew Rowan | In Review |  | *As a/an* retail investor, *I Want to* create AI models for stocks I’m interested in if they are not already in the application, *So That* I can use the model to predict prices | # When user has a stock selected that does not have an existing model, a training option will appear # When the training option is clicked, the application will train a new model and save it | # functionality to save and load trained models have been added and to check if the model has already been trained before has been implemented in this story MARKETMAG-75
Subtask | MARKETMAG-67 | Save LSTM model to local | Andrew Rowan | Done | Done
Subtask | MARKETMAG-63 | Add dynamic stock training/predicting in the backedn | Andrew Rowan | Done | Done | Whenever a user wishes to search a stock, it will automatically check if a saved model has been found and if not it will train a model for the user |  | # Created new function if views that separates page_test view and display_prediction view # created new path in urls.py for this new function # updated index.html
Subtask | MARKETMAG-58 | Develop attention function for LSTM model | Andrew Rowan | In Progress |  | abed support
Story | MARKETMAG-41 | Search for stocks other than those saved in "stocks" page | Henry Kim | Done | Done | *As a/an* retail investor, *I Want to* select a stock other than the presets in the stocks page, *So That* I can get price predictions from other stocks beside the presets | # In the search page, user can enter a stock ticker not displayed in the stocks page | # Created search page with a form that sends ticker string to backed end for processing. # Added APIView functon that validates string against csv of NASDAQ and NYSE stock tickers.
Subtask | MARKETMAG-51 | Decide which elements of the home page we want to implement | Henry Kim | Done | Done | Downselect homepage features for sprint 2. | # Select which features we want to implement for sprint 2 | # Selected navigation features to implement for sprint 2. # Updated story text to reflect the change. Separated other features to other stories.
Task | MARKETMAG-71 | Backlog Refinement | Henry Kim | Done | Done | Update sprint and product backlogs to reflect feedback given by the professor. | # Updated sprint backlog # Updated product backlog # Consensus from team | # Updated developer tasks in backlog, moved them as sub-tasks under appropriate user stories # Updated product backlog to have descriptions and acceptance criteria relative to professor’s feedback # Agreement met for reference story marketmag-47 and marketmag-39
Task | MARKETMAG-35 | Link prototype front end and back end | Henry Kim | Done | Done | Application front-end and back-end are currently two separate entities. This task will combine the two code bases into a single project | # React front-end and Django back-end codebases combined into single project codebase # Resolve merge conflicts from all team member code bases # Front end functions successfully interacts with back end using API calls. | # Helped team get all codebases into github repo # Added additional libraries that facilitates React interactivity with Rest APIs # Resolved merge conflicts # Was able to successfully test front end to back end interactivity through API end point and html requests
Task | MARKETMAG-33 | Sprint 2 Planning (project task) | Henry Kim | Done | Done | Conduct a planning session for sprint 2. Estimate points for stories/tasks and assign to backlog. | # Initial set of stories and tasks reviewed and accepted by dev team. # Recording of session for project artifact list | # Planning session done in online meeting # Recording created summarizing meeting artifacts in MS Teams
Story | MARKETMAG-72 | Create stocks page | Jonathan Sanchez | Done | Done | *As a* retail investor, *I Want* a webpage where I select stocks , *so that* I can train models and get price predictions | # When the user clicks on the stocks link, the browser should navigate to the stocks page # When the user clicks on home page link, the browser should navigate back to the hope page | # Implemented react router dom which uses links to navigate through the different pages. # Stocks page was created to conduction frontend to back end connection using html requests and API end point.
Story | MARKETMAG-39 | Get price prediction for a stock preset and displayed on the stocks page | Jonathan Sanchez | Done | Done | *As a/an* retail investor, *I Want to* get a price prediction from a preset stock on the stocks page, *So That* I can decide if I wish to buy, sell, or hold that stock | # In the stocks page, when a user clicks one of the displayed stocks, the application will present a price prediction along with recent price trends in a line chart | # MARKETMAG-65 - Converted logos into buttons. Added a loading message and risk prediction functions message # MARKETMAG-66 - Implemented function for risk predictions to communicate between frontend and backend. Also incorporated Abed's save & load functions within backend codebase.
Subtask | MARKETMAG-66 | Add backed support for display functions | Jonathan Sanchez | Done | Done | Need backend to process request from front end stocks page and send back risk assessments | # Backend processes stocks page sticker via logo buttons and returns risk assessment message. | # Implemented function for risk predictions to communicate between frontend and backend. Also incorporated Abed's save & load functions within backend codebase.
Subtask | MARKETMAG-65 | Add display capabilities to front end stocks page | Jonathan Sanchez | Done | Done | Demo stocks page only had logos and preset text. Add actual functionality to logos. | # Turn logos into buttons that sends data. Change preset text to display response data from backend. | # Converted logos into buttons. Added a loading message and risk prediction functions message.
Subtask | MARKETMAG-60 | Decide how were presenting results | Jonathan Sanchez | Done | Done | Decide how the stocks page will look | # A Stocks page format | # Review between Avi’s and Kassandra’s stock pages. # Decided to implement Avi’s page, but use Kassandra’s styling.
Story | MARKETMAG-73 | Create login page | Kassandra Camarillo | Done | Done | *As an* application user, *I Want* a webpage where I can enter my user credentials, *so that* I can securely log into my account | # When the user clicks on the login link the browser should navigate to the login page # When the user clicks on the homepage link, the browser should navigate to the home page | # Created a log-in page which a user will be directed to when log-in is selected on the navigation bar.
Story | MARKETMAG-69 | Create home page for user to navigate application | Kassandra Camarillo | Done | Done | *As a/an* retail investor, *I Want* a homepage, *So that* I can select where I can navigate to from the homepage | # When a user goes to the homepage, there will be links for the user to select to get to other pages | # Fixed the homepage to display the correct information and added working navigation links to take the user to all different pages.
Story | MARKETMAG-47 | Create user account/profile | Kassandra Camarillo | To Do |  | *As a/an* new user, *I Want to* create a user account with my own login name and password, *So that* I can securely log into the application | # When a user at the sign up page enters a unique account name and secure password in the account creation form, the application displays confirmation of account creation. # If and error occurs (name is not unique or password does not meet security minimums) display error to the user and ask to try again
Subtask | MARKETMAG-62 | Implement home page design updates | Kassandra Camarillo | Done | Done | Planning homepage layout based on initial homepage design. | # Homepage that can navigate between the different frontend pages. | # Created a header with links to each of the application’s pages.
Subtask | MARKETMAG-57 | Add log out functionality | Kassandra Camarillo | To Do
Subtask | MARKETMAG-56 | Add login functionality to homepage | Kassandra Camarillo | In Review |  | add andrew
Subtask | MARKETMAG-55 | Add user form page to application homepage | Kassandra Camarillo | To Do