## Tasks
Sprint 1 (9/25/24 - 10/22/24)
CLOSED
Task ID | Task Name | Parent ID | Parent Name | Parent URL | Status | Task Content | Assignee | Priority | Latest Comment | Comment Count | Assigned Comment Count | Due Date | Start Date | Date Created | Date Updated | Date Closed | Date Done | Created By | Space | Folder | List | tags | Lists | Sprints | Linked Tasks | Linked Docs | Time Logged | Time Logged Rolled Up | Time Estimate | Time Estimate Rolled Up | Points Estimate | Points Estimate Rolled Up | Acceptance Criteria (text)
8689rq8bh | Create User Stories |  |  |  | CLOSED | Create stories from user's perspectives (i.e. personas created for project). AC: List of user stories for each persona | Abed Mussawi, Andrew Rowan, Jonathan "Aviel" Sánchez, Kassandra Camarillo, Henry Kim | URGENT |  | 0 | 0 | 2024-09-28 |  | 2024-09-16 15:35 | 2024-09-28 21:32 | 2024-09-28 21:32 | 2024-09-28 21:32 | Henry Kim | Artificial Asynchrony | Dev Team | Sprint 1 (9/25/24 - 10/22/24) |  | Sprint 1 (9/25/24 - 10/22/24) | Sprint 1 (9/25/24 - 10/22/24) | [6 empty] | 0 | 20
8689vvadn | User stories - Abed | 8689rq8bh | Create User Stories | https://app.clickup.com/t/8689rq8bh | CLOSED |  | Abed Mussawi |  |  | 0 | 0 |  |  | 2024-09-22 16:21 | 2024-09-22 16:21 | 2024-09-28 21:32 |  | Henry Kim | Artificial Asynchrony | Dev Team | Sprint 1 (9/25/24 - 10/22/24) |  | Sprint 1 (9/25/24 - 10/22/24) | Sprint 1 (9/25/24 - 10/22/24) | [6 empty] | 4 | 4
8689vvaev | User stories - Andrew | 8689rq8bh | Create User Stories | https://app.clickup.com/t/8689rq8bh | CLOSED |  | Andrew Rowan |  |  | 0 | 0 |  |  | 2024-09-22 16:21 | 2024-09-22 16:22 | 2024-09-28 21:32 |  | Henry Kim | Artificial Asynchrony | Dev Team | Sprint 1 (9/25/24 - 10/22/24) |  | Sprint 1 (9/25/24 - 10/22/24) | Sprint 1 (9/25/24 - 10/22/24) | [6 empty] | 4 | 4
8689vvafe | User stories - Kassandra | 8689rq8bh | Create User Stories | https://app.clickup.com/t/8689rq8bh | CLOSED |  | Kassandra Camarillo |  |  | 0 | 0 |  |  | 2024-09-22 16:21 | 2024-09-22 16:22 | 2024-09-28 21:32 |  | Henry Kim | Artificial Asynchrony | Dev Team | Sprint 1 (9/25/24 - 10/22/24) |  | Sprint 1 (9/25/24 - 10/22/24) | Sprint 1 (9/25/24 - 10/22/24) | [6 empty] | 4 | 4
8689vvag1 | User stories - Henry | 8689rq8bh | Create User Stories | https://app.clickup.com/t/8689rq8bh | CLOSED |  | Henry Kim |  |  | 0 | 0 |  |  | 2024-09-22 16:22 | 2024-09-22 16:22 | 2024-09-28 21:32 |  | Henry Kim | Artificial Asynchrony | Dev Team | Sprint 1 (9/25/24 - 10/22/24) |  | Sprint 1 (9/25/24 - 10/22/24) | Sprint 1 (9/25/24 - 10/22/24) | [6 empty] | 4 | 4
8689vvagr | User stories - Avi | 8689rq8bh | Create User Stories | https://app.clickup.com/t/8689rq8bh | CLOSED |  | Jonathan "Aviel" Sánchez |  |  | 0 | 0 |  |  | 2024-09-22 16:22 | 2024-09-22 16:25 | 2024-09-28 21:32 |  | Henry Kim | Artificial Asynchrony | Dev Team | Sprint 1 (9/25/24 - 10/22/24) |  | Sprint 1 (9/25/24 - 10/22/24) | Sprint 1 (9/25/24 - 10/22/24) | [6 empty] | 4 | 4
8689vmj8q | Create Architecture Diagrams |  |  |  | CLOSED | Development team's task to generate set of architecture diagrams for sprint 1 The following lists the initial set of diagrams Architecture Diagram Context Diagram Sequence Diagram | Henry Kim, Andrew Rowan, Jonathan "Aviel" Sánchez, Kassandra Camarillo, Abed Mussawi | URGENT |  | 0 | 0 | 2024-10-05 | 2024-09-29 | 2024-09-21 11:59 | 2024-10-06 11:01 | 2024-10-06 11:01 | 2024-10-06 10:41 | Henry Kim | Artificial Asynchrony | Dev Team | Sprint 1 (9/25/24 - 10/22/24) |  | Sprint 1 (9/25/24 - 10/22/24) | Sprint 1 (9/25/24 - 10/22/24) | [7 empty] | 35 | Completed draft of the following diagrams in some diagramming software (Visio/Lucid Chart) Architecture Diagram Context Diagram Sequence Diagram
8689vmjbq | Conceptual Diagrams - Andrew | 8689vmj8q | Create Architecture Diagrams | https://app.clickup.com/t/8689vmj8q | CLOSED |  | Andrew Rowan |  |  | 0 | 0 |  |  | 2024-09-21 12:00 | 2024-10-06 11:01 | 2024-10-06 11:01 | 2024-10-06 11:01 | Henry Kim | Artificial Asynchrony | Dev Team | Sprint 1 (9/25/24 - 10/22/24) |  | Sprint 1 (9/25/24 - 10/22/24) | Sprint 1 (9/25/24 - 10/22/24) | [6 empty] | 7 | 7
8689vmjcp | Sequence Diagrams - Kassandra | 8689vmj8q | Create Architecture Diagrams | https://app.clickup.com/t/8689vmj8q | CLOSED |  | Kassandra Camarillo |  |  | 0 | 0 |  |  | 2024-09-21 12:00 | 2024-10-06 11:01 | 2024-10-06 11:01 | 2024-10-06 11:01 | Henry Kim | Artificial Asynchrony | Dev Team | Sprint 1 (9/25/24 - 10/22/24) |  | Sprint 1 (9/25/24 - 10/22/24) | Sprint 1 (9/25/24 - 10/22/24) | [6 empty] | 7 | 7
8689vv8aw | Conceptual Diagram - Henry | 8689vmj8q | Create Architecture Diagrams | https://app.clickup.com/t/8689vmj8q | CLOSED |  | Henry Kim |  |  | 0 | 0 |  |  | 2024-09-22 16:02 | 2024-10-06 11:01 | 2024-10-06 11:01 | 2024-10-06 11:01 | Henry Kim | Artificial Asynchrony | Dev Team | Sprint 1 (9/25/24 - 10/22/24) |  | Sprint 1 (9/25/24 - 10/22/24) | Sprint 1 (9/25/24 - 10/22/24) | [6 empty] | 7 | 7
8689vva4f | Sequence Diagrams - Avi | 8689vmj8q | Create Architecture Diagrams | https://app.clickup.com/t/8689vmj8q | CLOSED |  | Jonathan "Aviel" Sánchez |  |  | 0 | 0 |  |  | 2024-09-22 16:20 | 2024-10-06 11:01 | 2024-10-06 11:01 | 2024-10-06 11:01 | Henry Kim | Artificial Asynchrony | Dev Team | Sprint 1 (9/25/24 - 10/22/24) |  | Sprint 1 (9/25/24 - 10/22/24) | Sprint 1 (9/25/24 - 10/22/24) | [6 empty] | 7 | 7
8689vvacr | Sequence Diagram - Abed | 8689vmj8q | Create Architecture Diagrams | https://app.clickup.com/t/8689vmj8q | CLOSED |  | Abed Mussawi |  |  | 0 | 0 |  |  | 2024-09-22 16:21 | 2024-10-06 11:01 | 2024-10-06 11:01 | 2024-10-06 11:01 | Henry Kim | Artificial Asynchrony | Dev Team | Sprint 1 (9/25/24 - 10/22/24) |  | Sprint 1 (9/25/24 - 10/22/24) | Sprint 1 (9/25/24 - 10/22/24) | [6 empty] | 7 | 7
8689vnzrj | General research - Team study 7pts |  |  |  | CLOSED |  | Andrew Rowan |  |  | 0 | 0 |  |  | 2024-09-21 14:23 | 2024-10-22 13:13 | 2024-10-22 13:13 | 2024-10-21 16:29 | Henry Kim | Artificial Asynchrony | Dev Team | Sprint 1 (9/25/24 - 10/22/24) |  | Sprint 1 (9/25/24 - 10/22/24) | Sprint 1 (9/25/24 - 10/22/24) | [6 empty] | 7 | 7
IN DEVELOPMENT
Task ID | Task Name | Parent ID | Parent Name | Parent URL | Status | Task Content | Assignee | Priority | Latest Comment | Comment Count | Assigned Comment Count | Due Date | Start Date | Date Created | Date Updated | Date Closed | Date Done | Created By | Space | Folder | List | tags | Lists | Sprints | Linked Tasks | Linked Docs | Time Logged | Time Logged Rolled Up | Time Estimate | Time Estimate Rolled Up | Points Estimate | Points Estimate Rolled Up | Acceptance Criteria (text)
8689vmf0b | Update Wikipage |  |  |  | IN DEVELOPMENT |  | Henry Kim |  |  | 0 | 0 |  |  | 2024-09-21 11:42 | 2024-10-21 16:12 |  |  | Henry Kim | Artificial Asynchrony | Dev Team | Sprint 1 (9/25/24 - 10/22/24) |  | Sprint 1 (9/25/24 - 10/22/24) | Sprint 1 (9/25/24 - 10/22/24) | [6 empty] | 3 | 3
8689vmhbj | Add Sprint 1 videos/links | 8689vmf0b | Update Wikipage | https://app.clickup.com/t/8689vmf0b | IN DEVELOPMENT |  |  |  |  | 0 | 0 |  |  | 2024-09-21 11:54 | 2024-10-15 14:55 |  |  | Henry Kim | Artificial Asynchrony | Dev Team | Sprint 1 (9/25/24 - 10/22/24) |  | Sprint 1 (9/25/24 - 10/22/24) | Sprint 1 (9/25/24 - 10/22/24) | [7 empty] | 0
8689vmhh8 | Add Sprint 0 Completed Tasks | 8689vmf0b | Update Wikipage | https://app.clickup.com/t/8689vmf0b | DEPLOYED |  |  |  |  | 0 | 0 |  |  | 2024-09-21 11:55 | 2024-10-22 15:25 |  | 2024-10-22 15:25 | Henry Kim | Artificial Asynchrony | Dev Team | Sprint 1 (9/25/24 - 10/22/24) |  | Sprint 1 (9/25/24 - 10/22/24) | Sprint 1 (9/25/24 - 10/22/24) | [7 empty] | 0
8689vmhmh | Add Sprint 1 Burndown & Completed Tasks | 8689vmf0b | Update Wikipage | https://app.clickup.com/t/8689vmf0b | DEPLOYED |  |  |  |  | 0 | 0 |  |  | 2024-09-21 11:55 | 2024-10-22 15:25 |  | 2024-10-22 15:25 | Henry Kim | Artificial Asynchrony | Dev Team | Sprint 1 (9/25/24 - 10/22/24) |  | Sprint 1 (9/25/24 - 10/22/24) | Sprint 1 (9/25/24 - 10/22/24) | [7 empty] | 0
8689vmhqj | Add Sprint 1 Retro | 8689vmf0b | Update Wikipage | https://app.clickup.com/t/8689vmf0b | IN DEVELOPMENT |  |  |  |  | 0 | 0 |  |  | 2024-09-21 11:56 | 2024-10-15 14:55 |  |  | Henry Kim | Artificial Asynchrony | Dev Team | Sprint 1 (9/25/24 - 10/22/24) |  | Sprint 1 (9/25/24 - 10/22/24) | Sprint 1 (9/25/24 - 10/22/24) | [7 empty] | 0
8689vmhqp | Add Sprint 2 Planning | 8689vmf0b | Update Wikipage | https://app.clickup.com/t/8689vmf0b | IN DEVELOPMENT |  |  |  |  | 0 | 0 |  |  | 2024-09-21 11:56 | 2024-10-15 14:55 |  |  | Henry Kim | Artificial Asynchrony | Dev Team | Sprint 1 (9/25/24 - 10/22/24) |  | Sprint 1 (9/25/24 - 10/22/24) | Sprint 1 (9/25/24 - 10/22/24) | [7 empty] | 0
8689vmhtm | Add Architecture Diagrams | 8689vmf0b | Update Wikipage | https://app.clickup.com/t/8689vmf0b | DEPLOYED |  | Henry Kim |  |  | 0 | 0 |  |  | 2024-09-21 11:56 | 2024-10-22 15:25 |  | 2024-10-22 15:25 | Henry Kim | Artificial Asynchrony | Dev Team | Sprint 1 (9/25/24 - 10/22/24) |  | Sprint 1 (9/25/24 - 10/22/24) | Sprint 1 (9/25/24 - 10/22/24) | [7 empty] | 0
8689vmhuq | Add Product Personas | 8689vmf0b | Update Wikipage | https://app.clickup.com/t/8689vmf0b | DEPLOYED |  | Henry Kim |  |  | 0 | 0 |  |  | 2024-09-21 11:56 | 2024-10-21 16:13 |  | 2024-10-03 09:50 | Henry Kim | Artificial Asynchrony | Dev Team | Sprint 1 (9/25/24 - 10/22/24) |  | Sprint 1 (9/25/24 - 10/22/24) | Sprint 1 (9/25/24 - 10/22/24) | [7 empty] | 0
8689vmhvc | Add user stories | 8689vmf0b | Update Wikipage | https://app.clickup.com/t/8689vmf0b | DEPLOYED |  |  |  |  | 0 | 0 |  |  | 2024-09-21 11:56 | 2024-10-22 15:25 |  | 2024-10-22 15:25 | Henry Kim | Artificial Asynchrony | Dev Team | Sprint 1 (9/25/24 - 10/22/24) |  | Sprint 1 (9/25/24 - 10/22/24) | Sprint 1 (9/25/24 - 10/22/24) | [7 empty] | 0
8689vmhw4 | Add application test cases | 8689vmf0b | Update Wikipage | https://app.clickup.com/t/8689vmf0b | TO DO |  | Abed Mussawi |  |  | 0 | 0 |  |  | 2024-09-21 11:57 | 2024-10-21 16:13 |  |  | Henry Kim | Artificial Asynchrony | Dev Team | Sprint 1 (9/25/24 - 10/22/24) |  | Sprint 1 (9/25/24 - 10/22/24) | Sprint 1 (9/25/24 - 10/22/24) | [7 empty] | 0
8689tg07x | Create Prototype ~30 |  |  |  | IN DEVELOPMENT |  |  |  |  | 0 | 0 |  |  | 2024-09-17 16:09 | 2024-10-06 11:01 |  |  | Henry Kim | Artificial Asynchrony | Dev Team | Sprint 1 (9/25/24 - 10/22/24) |  | Sprint 1 (9/25/24 - 10/22/24) | Sprint 1 (9/25/24 - 10/22/24) | [7 empty] | 66
8689vmrx9 | Code for prototype, driven by user stories - Henry | 8689tg07x | Create Prototype ~30 | https://app.clickup.com/t/8689tg07x | DEPLOYED |  | Henry Kim |  |  | 0 | 0 |  |  | 2024-09-21 12:57 | 2024-10-21 16:14 |  | 2024-10-21 16:14 | Henry Kim | Artificial Asynchrony | Dev Team | Sprint 1 (9/25/24 - 10/22/24) |  | Sprint 1 (9/25/24 - 10/22/24) | Sprint 1 (9/25/24 - 10/22/24) | [6 empty] | 13 | 13
868ac72jb | Set up Django Environment | 8689vmrx9 | Code for prototype, driven by user stories - Henry | https://app.clickup.com/t/8689vmrx9 | DEPLOYED |  |  |  |  | 0 | 0 |  |  | 2024-10-21 16:19 | 2024-10-21 16:29 |  | 2024-10-21 16:29 | Henry Kim | Artificial Asynchrony | Dev Team | Sprint 1 (9/25/24 - 10/22/24) |  | Sprint 1 (9/25/24 - 10/22/24) | Sprint 1 (9/25/24 - 10/22/24) | [7 empty] | 0 | Short description of story/task deliverables/artifacts List of deliverable items (if necessary)
868ac756a | Create Views to test prediction generation | 8689vmrx9 | Code for prototype, driven by user stories - Henry | https://app.clickup.com/t/8689vmrx9 | DEPLOYED |  |  |  |  | 0 | 0 |  |  | 2024-10-21 16:21 | 2024-10-21 16:29 |  | 2024-10-21 16:29 | Henry Kim | Artificial Asynchrony | Dev Team | Sprint 1 (9/25/24 - 10/22/24) |  | Sprint 1 (9/25/24 - 10/22/24) | Sprint 1 (9/25/24 - 10/22/24) | [7 empty] | 0 | Short description of story/task deliverables/artifacts List of deliverable items (if necessary)
868ac76wq | Incorporate ML algorithm to Django | 8689vmrx9 | Code for prototype, driven by user stories - Henry | https://app.clickup.com/t/8689vmrx9 | DEPLOYED |  |  |  |  | 0 | 0 |  |  | 2024-10-21 16:22 | 2024-10-21 16:29 |  | 2024-10-21 16:29 | Henry Kim | Artificial Asynchrony | Dev Team | Sprint 1 (9/25/24 - 10/22/24) |  | Sprint 1 (9/25/24 - 10/22/24) | Sprint 1 (9/25/24 - 10/22/24) | [7 empty] | 0 | Short description of story/task deliverables/artifacts List of deliverable items (if necessary)
8689vmrzx | Create/Record Demo of Prototype | 8689tg07x | Create Prototype ~30 | https://app.clickup.com/t/8689tg07x | DEPLOYED |  | Henry Kim |  |  | 0 | 0 |  |  | 2024-09-21 12:57 | 2024-10-22 16:27 |  | 2024-10-22 16:27 | Henry Kim | Artificial Asynchrony | Dev Team | Sprint 1 (9/25/24 - 10/22/24) |  | Sprint 1 (9/25/24 - 10/22/24) | Sprint 1 (9/25/24 - 10/22/24) | [6 empty] | 1 | 1
8689vvd8z | Code for prototype, driven by user stories - Abed | 8689tg07x | Create Prototype ~30 | https://app.clickup.com/t/8689tg07x | DEPLOYED |  | Abed Mussawi |  |  | 0 | 0 |  |  | 2024-09-22 16:33 | 2024-10-21 16:14 |  | 2024-10-21 16:14 | Henry Kim | Artificial Asynchrony | Dev Team | Sprint 1 (9/25/24 - 10/22/24) |  | Sprint 1 (9/25/24 - 10/22/24) | Sprint 1 (9/25/24 - 10/22/24) | [6 empty] | 13 | 13
868ac75zy | Set up Postgre SQL database | 8689vvd8z | Code for prototype, driven by user stories - Abed | https://app.clickup.com/t/8689vvd8z | DEPLOYED |  |  |  |  | 0 | 0 |  |  | 2024-10-21 16:22 | 2024-10-21 16:29 |  | 2024-10-21 16:29 | Henry Kim | Artificial Asynchrony | Dev Team | Sprint 1 (9/25/24 - 10/22/24) |  | Sprint 1 (9/25/24 - 10/22/24) | Sprint 1 (9/25/24 - 10/22/24) | [7 empty] | 0 | Short description of story/task deliverables/artifacts List of deliverable items (if necessary)
868ac76gn | Create Initial Schema for Django Models | 8689vvd8z | Code for prototype, driven by user stories - Abed | https://app.clickup.com/t/8689vvd8z | DEPLOYED |  |  |  |  | 0 | 0 |  |  | 2024-10-21 16:22 | 2024-10-21 16:29 |  | 2024-10-21 16:29 | Henry Kim | Artificial Asynchrony | Dev Team | Sprint 1 (9/25/24 - 10/22/24) |  | Sprint 1 (9/25/24 - 10/22/24) | Sprint 1 (9/25/24 - 10/22/24) | [7 empty] | 0 | Short description of story/task deliverables/artifacts List of deliverable items (if necessary)
868ac76qd | Implement Models in Django | 8689vvd8z | Code for prototype, driven by user stories - Abed | https://app.clickup.com/t/8689vvd8z | DEPLOYED |  |  |  |  | 0 | 0 |  |  | 2024-10-21 16:22 | 2024-10-21 16:29 |  | 2024-10-21 16:29 | Henry Kim | Artificial Asynchrony | Dev Team | Sprint 1 (9/25/24 - 10/22/24) |  | Sprint 1 (9/25/24 - 10/22/24) | Sprint 1 (9/25/24 - 10/22/24) | [7 empty] | 0 | Short description of story/task deliverables/artifacts List of deliverable items (if necessary)
868ac76wz | Generate ERD Diagram | 8689vvd8z | Code for prototype, driven by user stories - Abed | https://app.clickup.com/t/8689vvd8z | DEPLOYED |  |  |  |  | 0 | 0 |  |  | 2024-10-21 16:22 | 2024-10-21 16:29 |  | 2024-10-21 16:29 | Henry Kim | Artificial Asynchrony | Dev Team | Sprint 1 (9/25/24 - 10/22/24) |  | Sprint 1 (9/25/24 - 10/22/24) | Sprint 1 (9/25/24 - 10/22/24) | [7 empty] | 0 | Short description of story/task deliverables/artifacts List of deliverable items (if necessary)
8689vvda5 | Code for prototype, driven by user stories - Andrew | 8689tg07x | Create Prototype ~30 | https://app.clickup.com/t/8689tg07x | DEPLOYED |  | Andrew Rowan |  |  | 0 | 0 |  |  | 2024-09-22 16:33 | 2024-10-21 16:14 |  | 2024-10-21 16:14 | Henry Kim | Artificial Asynchrony | Dev Team | Sprint 1 (9/25/24 - 10/22/24) |  | Sprint 1 (9/25/24 - 10/22/24) | Sprint 1 (9/25/24 - 10/22/24) | [6 empty] | 13 | 13
868ac77ah | Implement Trading strategy algorithm | 8689vvda5 | Code for prototype, driven by user stories - Andrew | https://app.clickup.com/t/8689vvda5 | DEPLOYED |  |  |  |  | 0 | 0 |  |  | 2024-10-21 16:23 | 2024-10-21 16:29 |  | 2024-10-21 16:29 | Henry Kim | Artificial Asynchrony | Dev Team | Sprint 1 (9/25/24 - 10/22/24) |  | Sprint 1 (9/25/24 - 10/22/24) | Sprint 1 (9/25/24 - 10/22/24) | [7 empty] | 0 | Short description of story/task deliverables/artifacts List of deliverable items (if necessary)
868ac78xp | Implement ML model training algorithm | 8689vvda5 | Code for prototype, driven by user stories - Andrew | https://app.clickup.com/t/8689vvda5 | DEPLOYED |  |  |  |  | 0 | 0 |  |  | 2024-10-21 16:24 | 2024-10-21 16:29 |  | 2024-10-21 16:29 | Henry Kim | Artificial Asynchrony | Dev Team | Sprint 1 (9/25/24 - 10/22/24) |  | Sprint 1 (9/25/24 - 10/22/24) | Sprint 1 (9/25/24 - 10/22/24) | [7 empty] | 0 | Short description of story/task deliverables/artifacts List of deliverable items (if necessary)
868ac7aam | Implement ML model prediction logic | 8689vvda5 | Code for prototype, driven by user stories - Andrew | https://app.clickup.com/t/8689vvda5 | DEPLOYED |  |  |  |  | 0 | 0 |  |  | 2024-10-21 16:26 | 2024-10-21 16:29 |  | 2024-10-21 16:29 | Henry Kim | Artificial Asynchrony | Dev Team | Sprint 1 (9/25/24 - 10/22/24) |  | Sprint 1 (9/25/24 - 10/22/24) | Sprint 1 (9/25/24 - 10/22/24) | [7 empty] | 0 | Short description of story/task deliverables/artifacts List of deliverable items (if necessary)
8689vvdaq | Code for prototype, driven by user stories - Avi | 8689tg07x | Create Prototype ~30 | https://app.clickup.com/t/8689tg07x | IN DEVELOPMENT |  | Jonathan "Aviel" Sánchez |  |  | 0 | 0 |  |  | 2024-09-22 16:33 | 2024-10-15 14:56 |  |  | Henry Kim | Artificial Asynchrony | Dev Team | Sprint 1 (9/25/24 - 10/22/24) |  | Sprint 1 (9/25/24 - 10/22/24) | Sprint 1 (9/25/24 - 10/22/24) | [6 empty] | 13 | 13
868ac7c9y | Generate user stock selection and display page | 8689vvdaq | Code for prototype, driven by user stories - Avi | https://app.clickup.com/t/8689vvdaq | BACKLOG |  |  |  |  | 0 | 0 |  |  | 2024-10-21 16:27 | 2024-10-21 16:27 |  |  | Henry Kim | Artificial Asynchrony | Dev Team | Sprint 1 (9/25/24 - 10/22/24) |  | Sprint 1 (9/25/24 - 10/22/24) | Sprint 1 (9/25/24 - 10/22/24) | [7 empty] | 0 | Short description of story/task deliverables/artifacts List of deliverable items (if necessary)
8689vvdbe | Code for prototype, driven by user stories - Kassandra | 8689tg07x | Create Prototype ~30 | https://app.clickup.com/t/8689tg07x | IN REVIEW |  | Kassandra Camarillo |  |  | 0 | 0 |  |  | 2024-09-22 16:34 | 2024-10-21 16:14 |  |  | Henry Kim | Artificial Asynchrony | Dev Team | Sprint 1 (9/25/24 - 10/22/24) |  | Sprint 1 (9/25/24 - 10/22/24) | Sprint 1 (9/25/24 - 10/22/24) | [6 empty] | 13 | 13
868ac7bx8 | Create preliminary design for site homepage | 8689vvdbe | Code for prototype, driven by user stories - Kassandra | https://app.clickup.com/t/8689vvdbe | DEPLOYED |  |  |  |  | 0 | 0 |  |  | 2024-10-21 16:27 | 2024-10-21 16:29 |  | 2024-10-21 16:29 | Henry Kim | Artificial Asynchrony | Dev Team | Sprint 1 (9/25/24 - 10/22/24) |  | Sprint 1 (9/25/24 - 10/22/24) | Sprint 1 (9/25/24 - 10/22/24) | [7 empty] | 0 | Short description of story/task deliverables/artifacts List of deliverable items (if necessary)
868ac7cah | Generate homepage with React | 8689vvdbe | Code for prototype, driven by user stories - Kassandra | https://app.clickup.com/t/8689vvdbe | IN REVIEW |  |  |  |  | 0 | 0 |  |  | 2024-10-21 16:27 | 2024-10-21 16:29 |  |  | Henry Kim | Artificial Asynchrony | Dev Team | Sprint 1 (9/25/24 - 10/22/24) |  | Sprint 1 (9/25/24 - 10/22/24) | Sprint 1 (9/25/24 - 10/22/24) | [7 empty] | 0 | Short description of story/task deliverables/artifacts List of deliverable items (if necessary)
8689rq9m4 | Update Presentation |  |  |  | IN DEVELOPMENT |  | Henry Kim |  |  | 0 | 0 |  |  | 2024-09-16 15:36 | 2024-10-06 11:01 |  |  | Henry Kim | Artificial Asynchrony | Dev Team | Sprint 1 (9/25/24 - 10/22/24) |  | Sprint 1 (9/25/24 - 10/22/24) | Sprint 1 (9/25/24 - 10/22/24) | [6 empty] | 3 | 3
8689vmgce | Professor Feedback slides | 8689rq9m4 | Update Presentation | https://app.clickup.com/t/8689rq9m4 | DEPLOYED |  |  |  |  | 0 | 0 |  |  | 2024-09-21 11:50 | 2024-10-21 16:16 |  | 2024-10-21 16:16 | Henry Kim | Artificial Asynchrony | Dev Team | Sprint 1 (9/25/24 - 10/22/24) |  | Sprint 1 (9/25/24 - 10/22/24) | Sprint 1 (9/25/24 - 10/22/24) | [7 empty] | 0
8689vmgdf | MVP slide | 8689rq9m4 | Update Presentation | https://app.clickup.com/t/8689rq9m4 | DEPLOYED |  | Henry Kim |  |  | 0 | 0 |  |  | 2024-09-21 11:50 | 2024-10-22 15:26 |  | 2024-10-22 15:26 | Henry Kim | Artificial Asynchrony | Dev Team | Sprint 1 (9/25/24 - 10/22/24) |  | Sprint 1 (9/25/24 - 10/22/24) | Sprint 1 (9/25/24 - 10/22/24) | [7 empty] | 0
8689vmgna | Diagrams slides | 8689rq9m4 | Update Presentation | https://app.clickup.com/t/8689rq9m4 | DEPLOYED |  | Abed Mussawi |  |  | 0 | 0 |  |  | 2024-09-21 11:51 | 2024-10-22 15:26 |  | 2024-10-22 15:26 | Henry Kim | Artificial Asynchrony | Dev Team | Sprint 1 (9/25/24 - 10/22/24) |  | Sprint 1 (9/25/24 - 10/22/24) | Sprint 1 (9/25/24 - 10/22/24) | [7 empty] | 0
8689vmgqf | Product Backlog slides | 8689rq9m4 | Update Presentation | https://app.clickup.com/t/8689rq9m4 | DEPLOYED |  | Henry Kim |  |  | 0 | 0 |  |  | 2024-09-21 11:51 | 2024-10-22 15:26 |  | 2024-10-22 15:26 | Henry Kim | Artificial Asynchrony | Dev Team | Sprint 1 (9/25/24 - 10/22/24) |  | Sprint 1 (9/25/24 - 10/22/24) | Sprint 1 (9/25/24 - 10/22/24) | [7 empty] | 0
8689vmgyg | Sprint 1 Backlog slides | 8689rq9m4 | Update Presentation | https://app.clickup.com/t/8689rq9m4 | DEPLOYED |  | Henry Kim |  |  | 0 | 0 |  |  | 2024-09-21 11:52 | 2024-10-22 15:26 |  | 2024-10-22 15:26 | Henry Kim | Artificial Asynchrony | Dev Team | Sprint 1 (9/25/24 - 10/22/24) |  | Sprint 1 (9/25/24 - 10/22/24) | Sprint 1 (9/25/24 - 10/22/24) | [7 empty] | 0
8689vmh2j | Metrics slide | 8689rq9m4 | Update Presentation | https://app.clickup.com/t/8689rq9m4 | DEPLOYED |  | Henry Kim |  |  | 0 | 0 |  |  | 2024-09-21 11:53 | 2024-10-22 15:26 |  | 2024-10-22 15:26 | Henry Kim | Artificial Asynchrony | Dev Team | Sprint 1 (9/25/24 - 10/22/24) |  | Sprint 1 (9/25/24 - 10/22/24) | Sprint 1 (9/25/24 - 10/22/24) | [7 empty] | 0
8689vmh51 | Project Demo slide | 8689rq9m4 | Update Presentation | https://app.clickup.com/t/8689rq9m4 | DEPLOYED |  |  |  |  | 0 | 0 |  |  | 2024-09-21 11:53 | 2024-10-22 15:26 |  | 2024-10-22 15:26 | Henry Kim | Artificial Asynchrony | Dev Team | Sprint 1 (9/25/24 - 10/22/24) |  | Sprint 1 (9/25/24 - 10/22/24) | Sprint 1 (9/25/24 - 10/22/24) | [7 empty] | 0
868ac70k9 | Update Tech and Algorithm Slides | 8689rq9m4 | Update Presentation | https://app.clickup.com/t/8689rq9m4 | DEPLOYED |  | Andrew Rowan |  |  | 0 | 0 |  |  | 2024-10-21 16:17 | 2024-10-22 15:26 |  | 2024-10-22 15:26 | Henry Kim | Artificial Asynchrony | Dev Team | Sprint 1 (9/25/24 - 10/22/24) |  | Sprint 1 (9/25/24 - 10/22/24) | Sprint 1 (9/25/24 - 10/22/24) | [7 empty] | 0 | Short description of story/task deliverables/artifacts List of deliverable items (if necessary)
8689tg295 | Sprint 1 Retro |  |  |  | IN DEVELOPMENT |  | Henry Kim |  |  | 0 | 0 | 2024-10-19 | 2024-10-19 | 2024-09-17 16:13 | 2024-10-22 15:25 |  |  | Henry Kim | Artificial Asynchrony | Dev Team | Sprint 1 (9/25/24 - 10/22/24) |  | Sprint 1 (9/25/24 - 10/22/24) | Sprint 1 (9/25/24 - 10/22/24) | [6 empty] | 2 | 2
8689tg2fj | Presentation Recording |  |  |  | IN DEVELOPMENT |  | Abed Mussawi, Kassandra Camarillo, Jonathan "Aviel" Sánchez, Andrew Rowan, Henry Kim |  |  | 0 | 0 | 2024-10-21 | 2024-10-21 | 2024-09-17 16:13 | 2024-10-21 16:11 |  |  | Henry Kim | Artificial Asynchrony | Dev Team | Sprint 1 (9/25/24 - 10/22/24) |  | Sprint 1 (9/25/24 - 10/22/24) | Sprint 1 (9/25/24 - 10/22/24) | [7 empty] | 0
TO DO
Task ID | Task Name | Parent ID | Parent Name | Parent URL | Status | Task Content | Assignee | Priority | Latest Comment | Comment Count | Assigned Comment Count | Due Date | Start Date | Date Created | Date Updated | Date Closed | Date Done | Created By | Space | Folder | List | tags | Lists | Sprints | Linked Tasks | Linked Docs | Time Logged | Time Logged Rolled Up | Time Estimate | Time Estimate Rolled Up | Points Estimate | Points Estimate Rolled Up | Acceptance Criteria (text)
8689rq8gn | Create Test Cases (needs AC) |  |  |  | TO DO |  | Andrew Rowan |  |  | 0 | 0 |  |  | 2024-09-16 15:35 | 2024-10-09 10:43 |  |  | Henry Kim | Artificial Asynchrony | Dev Team | Sprint 1 (9/25/24 - 10/22/24) |  | Sprint 1 (9/25/24 - 10/22/24) | Sprint 1 (9/25/24 - 10/22/24) | [7 empty] | 0
868ac7cra | Connect front end and back end code for prototype |  |  |  | TO DO |  |  |  |  | 0 | 0 |  |  | 2024-10-21 16:28 | 2024-10-21 16:28 |  |  | Henry Kim | Artificial Asynchrony | Dev Team | Sprint 1 (9/25/24 - 10/22/24) |  | Sprint 1 (9/25/24 - 10/22/24) | Sprint 1 (9/25/24 - 10/22/24) | [7 empty] | 0 | Short description of story/task deliverables/artifacts List of deliverable items (if necessary)