## Tasks
Sprint 0
CLOSED
Task ID | Task Name | Parent ID | Parent Name | Parent URL | Status | Task Content | Assignee | Priority | Latest Comment | Comment Count | Assigned Comment Count | Due Date | Start Date | Date Created | Date Updated | Date Closed | Date Done | Created By | Space | Folder | List | tags | Lists | Sprints | Linked Tasks | Linked Docs | Time Logged | Time Logged Rolled Up | Time Estimate | Time Estimate Rolled Up | Points Estimate | Points Estimate Rolled Up
8689rq4uc | Presentation Recording (Team) |  |  |  | CLOSED |  |  |  |  | 0 | 0 | 2024-09-23 23:59 | 2024-09-23 | 2024-09-16 15:32 | 2024-09-25 11:58 | 2024-09-25 11:58 | 2024-09-25 11:58 | Henry Kim | Artificial Asynchrony | Dev Team | Sprint 0 |  | Sprint 0 | [8 empty] | 0
8689rq4tj | Create Team Wiki page (Kassandra) |  |  |  | CLOSED |  | Kassandra Camarillo |  |  | 0 | 0 | 2024-09-24 | 2024-09-16 | 2024-09-16 15:32 | 2024-09-25 11:58 | 2024-09-25 11:58 | 2024-09-25 11:58 | Henry Kim | Artificial Asynchrony | Dev Team | Sprint 0 |  | Sprint 0 | [8 empty] | 0
8689rq4te | Create Sprint 0 Powerpoint (Team) |  |  |  | CLOSED |  | Abed Mussawi |  |  | 0 | 0 | 2024-09-22 | 2024-09-16 | 2024-09-16 15:32 | 2024-09-25 11:58 | 2024-09-25 11:58 | 2024-09-25 11:58 | Henry Kim | Artificial Asynchrony | Dev Team | Sprint 0 |  | Sprint 0 | [8 empty] | 0
8689t161p | Problem statement, Description, Technologies, Algorithms (Andrew & Abed) | 8689rq4te | Create Sprint 0 Powerpoint (Team) | https://app.clickup.com/t/8689rq4te | CLOSED | Slides for sprint 0 presentation. Working together with | Andrew Rowan |  |  | 0 | 0 | 2024-09-22 | 2024-09-16 | 2024-09-16 23:05 | 2024-09-23 10:19 | 2024-09-25 11:58 | 2024-09-23 10:19 | Henry Kim | Artificial Asynchrony | Dev Team | Sprint 0 |  | Sprint 0 | [8 empty] | 0
8689t16d4 | Project Schedule, Cadence/Colab Description (Henry) | 8689rq4te | Create Sprint 0 Powerpoint (Team) | https://app.clickup.com/t/8689rq4te | CLOSED |  | Henry Kim |  |  | 0 | 0 | 2024-09-22 | 2024-09-16 | 2024-09-16 23:06 | 2024-09-23 10:19 | 2024-09-25 11:58 | 2024-09-23 10:19 | Henry Kim | Artificial Asynchrony | Dev Team | Sprint 0 |  | Sprint 0 | [8 empty] | 0
8689t16f2 | Team Working Agreement Slides (Aviel) | 8689rq4te | Create Sprint 0 Powerpoint (Team) | https://app.clickup.com/t/8689rq4te | CLOSED | Subtask for slide as part of sprint 0 presentation | Jonathan "Aviel" Sánchez |  |  | 0 | 0 | 2024-09-22 | 2024-09-16 | 2024-09-16 23:06 | 2024-09-24 08:51 | 2024-09-25 11:58 | 2024-09-24 08:51 | Henry Kim | Artificial Asynchrony | Dev Team | Sprint 0 |  | Sprint 0 | [8 empty] | 0
8689t16mz | Agenda, Team Roles, Wiki (Kassandra) | 8689rq4te | Create Sprint 0 Powerpoint (Team) | https://app.clickup.com/t/8689rq4te | CLOSED |  | Kassandra Camarillo |  |  | 0 | 0 | 2024-09-22 | 2024-09-16 | 2024-09-16 23:07 | 2024-09-23 10:19 | 2024-09-25 11:58 | 2024-09-23 10:19 | Henry Kim | Artificial Asynchrony | Dev Team | Sprint 0 |  | Sprint 0 | [8 empty] | 0
8689vmfn8 | Sprint Retro Slide | 8689rq4te | Create Sprint 0 Powerpoint (Team) | https://app.clickup.com/t/8689rq4te | CLOSED |  | Henry Kim |  |  | 0 | 0 | 2024-09-22 | 2024-09-21 | 2024-09-21 11:46 | 2024-09-23 10:19 | 2024-09-25 11:58 | 2024-09-23 10:19 | Henry Kim | Artificial Asynchrony | Dev Team | Sprint 0 |  | Sprint 0 | [8 empty] | 0
8689rq4u2 | Sprint0 Retro & Sprint1 Planning Recording (Henry) |  |  |  | CLOSED |  | Henry Kim |  |  | 0 | 0 | 2024-09-21 | 2024-09-16 | 2024-09-16 15:32 | 2024-09-25 11:58 | 2024-09-25 11:58 | 2024-09-23 10:20 | Henry Kim | Artificial Asynchrony | Dev Team | Sprint 0 |  | Sprint 0 | [8 empty] | 0
8689rq4tt | Create Team Working Agreement (Aviel) |  |  |  | CLOSED |  | Jonathan "Aviel" Sánchez |  |  | 0 | 0 | 2024-09-24 | 2024-09-14 | 2024-09-16 15:32 | 2024-09-25 11:58 | 2024-09-25 11:58 | 2024-09-23 10:20 | Henry Kim | Artificial Asynchrony | Dev Team | Sprint 0 |  | Sprint 0 | [8 empty] | 0